Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 08-12-2025 |
| --- | --- |
| Team ID (SkillWallet ID) | SWUID202560126 |
| Project Name | Freelancing Application |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Product Backlog & Sprint Schedule:

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Authentication | USN-1 | As a user, I can sign up and log in securely. | 3 | High | Simramary |
|  | User Authentication | USN-2 | As a user, I can reset my password. | 2 | Medium | Simramary |
|  | User Profile (Client/Freelancer) | USN-3 | As a user, I can update my basic profile details. | 2 | Medium | Simramary |
|  | Role Management | USN-4 | As a user, I can select my role as Client or Freelancer. | 1 | High | Simramary |
| Sprint-2 | Project Posting | USN-5 | As a client, I can post a freelance job. | 3 | High | Simramary |
|  | Job Browsing | USN-6 | As a freelancer, I can browse and filter jobs | 3 | High | Simramary |
|  | Proposals/ Bidding | USN-7 | As a freelancer, I can apply(bid) for a project. | 2 | High | Simramary |
|  | View Proposals | USN-8 | As a client, I can view all proposals for my project | 2 | High | Simramary |
| Sprint-3 | Messaging/ Chat | USN-9 | As a user, I can send and receive messages | 3 | Medium | Simramary |
|  | Work Submission | USN-10 | As a freelancer, I can upload completed project work | 2 | High | Simramary |
|  | Review& Rating | USN-11 | As a client, I can rate and review freelancers. | 2 | Medium | Simramary |
|  | Account Security | USN-12 | As a user, I can change my password | 1 | Medium | Simramary |

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 08 | 5 Days | 25 Nov 2025 | 29 Nov 2025 | 08 | 25 Nov 2025 |
| Sprint-2 | 10 | 5 Days | 30 Nov 2025 | 04 Dec 2025 | 10 | 04 Dec 2025 |
| Sprint-3 | 08 | 4 Days | 5 Dec 2025 | 08 Dec 2025 | 08 | 08 Dec 2025 |